## Project Management SOW
STATEMENT OF WORK
ORGANIZATION
CLIENT NAME | Carlos Guerrero
CLIENT PHONE
CLIENT EMAIL
CLIENT MAILING ADDRESS
DATE |  | AUTHOR:
PROJECT
PROJECT NAME | PrinterBI API
Technology Used | ASP.NET Core web API 2.1 , C#, Postgres, Entityframework
Project Architecture | 3 tier architectecure with Data access layer, Business layer and presentation layer
API Format | JSON
DESCRIPTION
Porject delivery and milestone
DELIVERABLE DATE DUE | DELIVERABLE DESCRIPTION
2019-06-07 | The development will start from 1st May 2019.
Project Hours and Cost
DESCRIPTION | Hours | Cost
Total Admin panel APIs | 180 | $ 7/hour
TOTAL COST |  | 1260
BUSINESS TERMS / CONDITIONS
TERMS OF PAYMENT
20% upfront payment.
The project is devided into 4 milestones. Each milestone is of 45 hours. Payment needs to be done after each milestone completion
TERMINATION
15 days prior notice should be given before termination for any reason. In case of termination client should pay all the services provided up to and including
the date of termination or expiration.
AUTHORIZATION
CLIENT SIGNATURE
CLIENT PRINTED NAME
CLIENT DATE
PROVIDER SIGNATURE
PROVIDER PRINTED NAME
PROVIDER DATE

## - Disclaimer - (hidden)
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.

## Estimated hours
Milestones | Module | Functionality | Hours | Remarks | Delivery resources | Delivery date
Milestone 1 | Project Structure | Make a project structure for API In ASP.NET Core | 24 | As here for each customer DB connectin details are different we have to differently connect to each DB & get informatin which needs more efforts | At the end of the Milestone 1 it must be delivered a resource where an user and a password can be passed and the resource validate if those credentials are stored in the DB. Likewise, there must be other URLs where the functionalities described in the milestone could be seen. | 13/5/2019
Swagger integration
Authentication & Authorization method implementation
Service layer
Connection with DB
| Login Module | Login - validate user credentials - Token based authorization which helps in security terms | 16
Forgot Password
Reset Password
Change Password
Dynamic menu generation as per User RoleRights
Milestone 2 | Moved from Admin to Customer | Provision tenant - Make all required table in customer DB & other logic implementation | 30 |  | At the end of the Milestone 2 a resource must be provided where a customer can be passed and the resource generate all the procedures needed to establish a new customer site. | 29/05/2019
DeProvision tenant - Remove all tables from customer DB & other logic information
Upload Department file to customer DB + with rolerights & parent child department logic
Upload User file to customer DB
| DB Migration | Migrating the database functionality from SQL Server to Postgres | 40
Dynamic database support
Migrating the Stored Procedure logic from SQL Server to Postgres
Milestone 3 | Validate Tenant | Check the request coming from the server is valid host or not & check is it a valid tenant or not | 30 | All the main logic to redirect the customer tenant to correct tenant & seprate out each tenant to implemenet multitenant structure logic rest here | At the end of the Milestone 3 it must be provided a resource where all the functionalities described in the milestone could be performed. | 2019-06-06
if request coming from valid tenant then get all required informatin for that particular tenant like DB information & other
| Common | Department list | 4
Role rights list
| Dashboard | Get Assigned report list to logic user | 6
For redirection to power bi report fetch required data for power bi like power bi report id
Milestone 4 | sync reports | fetch data from power bi + inser/update in DB | 6 |  | At the end of the Milestone 4 it must be provided a resource where all the functionalities described in the milestone could be performed. | 14/6/2019
| User | Listing of User | 8
Insert user information
Update user information
Detele user information
| Assign Reports to all | Get report list with assigned reports also | 6
Update assigned reports to all user information
| Assign reports to uer | user list with applied filter | 10
get assigned report & other reports for that particualar user
update assign report to user
| Total |  | 180